## Week3-Project Plan
Task Name | Description | Due Date | Owner | Status
Creating Lo-fi wireframe | Creating a sketch design on ideally what the web app should look like without using any colours, or text details. Instead, we used placeholders and different type of elements. | 1/27/2023 | Lorenz, Ryan | In Progress
Final Wireframe | Finalizing full wireframe | 1/27/2023 |  | To-do
Final Workflow | Finalizing workflow for team members | 1/21/2023 | Steven | To-do
Finalizing scope | Finalizing the details of project scope and working out initial prototype | 1/21/2023 | Steven | To-do
Creating Hi-fi wireframe | Creating a final design based on the lo-fi wireframe which will help on how the web app will turn to look as we're coding it | 1/27/2023 | Lorenz, Ryan | In Progress
Creating backend schema | Making the back-end schema for the relationals of the website (mongo ref) | 1/20/2023 | Aj, Emil | Done
User stories | Proposal user story Plan A and Plan B for the Co-op page but we need to finalize it with the client |  | Lorenz, Ryan,Steven,Emil,Aj | Done
UI Flow | Creating a frontend UI design flow | 1/20/2023 | Steven, Ryan, Lorenz | Done
Backend database logic flow | Created flow for database schema | 1/21/2023 | Aj,Emil | Done
Base project Initialization | Creating a intial code base and pushing to github repo |  | Aj, Emil | Done
Stakeholder research | Talking to stakeholders for further input on design and codebase | 1/27/2023 | Steven | To-do
Creating landing page | Creating landing page for co op pages |  | Ryan,Lorenz | To-do
Database refinement | Adding functions to backend schema |  | Aj,Emil | To-do
Final Design | Looking at different schools co op pages and learning about the different design patterns they've used and implementing what we can on our co op page. Also talking to diferent keyholders to take in their inputs and implement on our co op pages. | 1/27/2023 | Steven,Ryan,Emil,Lorenz,Aj | To-do
Code the design for the job postings | Implement the code for the design portion of the job postings page |  |  | To-do
Code the design for the job search page |  |  |  | To-do
Code the design for the create profile page |  |  |  | To-do
UX research/interviews | Holding interviews for user research and testing of prototype page | 2/24/2023 | Steven | To-do
Implement MERN with Next.js | Utilizing mongoDB database, Express.js, React with next.js, Node.js |  | Steven, Ryan, Lorenz, Emil,Aj | To-do
Initializing codebase and connecting features | Implements ESlint | 2023-01-20 | Emil | Done
Testing prototype of co op page | Testing functional prototype |  | Steven | To-do
User story - Student using co op page | Implements MongoDB | 2023-02-03 | Emil | Done
User story - Company posting job | Implements Cloudinary | 2023-02-03 | Emil | Done
User story - Faculty admitting and registering job postings | Make Schema for (Job Posting and Company) | 2023-02-03 | AJ | To-do
User story - Student registered on co op page | Make Schema for Student |  |  | To-do

## Dependencies and Tech Stack
Dependencies
SSO Services from Microsoft | Using verification and validation services for user login
MongoDB Student Database | Read, Write, Query data for students
Read from VCC student database
Cloudinary | Photo uploading and storage for student resumes, school banners, company logos
Youtube API | Video storage for school co op videos, and uploading of co op videos
Tech Stack
Reactjs
TailwindCSS
SASS *
Next.JS
Tyepscript
MongoDB
Mongoose